## Sheet1
|  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March
|  | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4 | W 1 | W 2 | W 3 | W 4
1 | Planning and Organizing
Skill Assessment
Gathering Capstone Ideas
2 | Problem Identification
Assess Current State of the Problem
Formulation of the Solution
Conceptualizing the Project
3 | Requirement Gathering
Knowledge Assessment
Defining the Scope of the Game
Defining the specifics of the game
Writing a Storyline
Developing tools assessment
Define target software and hardware
4 | Design
Character Design
World Design
Interface Design
Preliminary Prototype
5 | Development
Character Animation
Programming and Scripting the Game
Creating Cut-Scenes
Assembling the Game
6 | Testing
Debugging Errors
Testing on Devices
User Testing
Evaluating through survey
7 | Deployment
Releasing the Game
Uploading the Game
Assess the Outcome of the Game
Support the Game