## Sheet1
Advising Summary | [5 empty] | Advising Info
Bugs | Description | Severity | Status | Covered by | Developers Note | Date: January 22, 2017
Game over screen | Game over screen still not implemented, pauses the game | 5 | Unvisted |  |  | Adviser:
Load Game | Loading a game does not work | 5 | Unvisited |  |  | Dean UMOSO, Danny G.
Camera Rotation | Very uncomfortable automatic movevment in camera | 5 | On Going |  | Harold | Prof. ELLANA Reggie
Game Instructions | Game must have instructions | 4 | Unvisited
Game Tutorials | Game must have tutorials | 4 | Unvisited |  |  | Severity Table
Maps and directions for quests | Maps or directions is needed for more information to the player | 4 | Unvisited |  |  | Degree | Interpretation
Dialogue Overlaps | Dialogue overlaps certain part of gameplay | 4 | Unvisted |  |  | 1 | Slight glitch, Minor error
Objectives | Objectives cannot be seen by player | 3 | Unvisted |  |  | 2 | Possible major error
Collection Quest Update | There must be an update on collection quests ex. Find Bag 0/1, also must have another description if done and not end instant | 3 | Unvisited |  |  | 3 | Creates unease to player
Instruction placement | Instructions must not be placed in dialogue box | 3 | Unvisited |  |  | 4 | Irritating glitches
Main must be centered | Main function in code blocks must be centered | 3 | Unvisited |  |  | 5 | Makes game unplayable
Blocks clicked is not placed | Tapped blocks does not scale with canvas | 3 | Unvisited
Introductions of Characters | The game must have proper introduction to characters | 3 | Unvisited |  |  | Status Table
Pause game too Big UI | Pause game have big UI | 3 | Unvisited |  |  | Values | Interpretation
Playing game on Dialogue | Game is played on dialogue causing events to happen while reading the dialogue | 3 | Unvisted |  |  | Unvisited | still has bug
Small labels | Manu has small labels and almost unreadable | 2 | Unvisted |  |  | On Going | Debugging the game
Storyboard | storyboard must be included in the documentations | 2 | Unvisited | Diana | Diana | Fixed | Bug free Yay!
Kidnap Nexo's friends | The kidnapping of Psuedo and Pheta enemy dialogue must be improved | 2 | Unvisited
Cancelation of Special Blocks | If and repeat blocks must be allowed to cancel | 2 | Unvisited
Better Transitions | Transitions must be improved | 2 | Unvisited
Interaction | Interaction with NPC may be improved | 1 | Unvisted |  | Tap to Interact as a start trigger
Game Description | Game description is not complete "W1S1" | 1 | Unvisted |  | Should be whole
Compiler Feel | Compiling for UX | 1 | Unvisited